## Tasks
Task ID | Task Name | Bucket Name | Progress | Priority | Assigned To | Created By | Created Date | Start Date | Due Date | Late | Completed Date | Completed By | Description | Completed Checklist Items | Checklist Items | Labels
CX2iFKtHu06fpQtjcinir2QAGM2D | Draft Style Guide | Style Guide Development | Not started | Medium | Matthew Schuster | Matthew Schuster | 12/13/2021 |  | 12/20/2021 | false
Ai6uwMCl0ka3qu8Xv7suOmQAMBWq | Incorporate Style Guide Feedback | Style Guide Development | In progress | Medium | Matthew Schuster | Matthew Schuster | 12/13/2021 | 12/14/2021 | 12/27/2021 | false |  |  |  | 2/6 | Provide final feedback deadline prior to finalization of style guide;Document feedback from all stakeholders;Send email to all stakeholders for feedback;Implement and circulate style guide with initial communication;Send reminder emails to all stakeholders who have not submitted feedback;Incorporate feedback into style guide draft and re-circulate | Green
DJSdH2bq20mAaZlX7SCJQmQAFUS9 | Publish first official communication with new Style Guide | Style Guide Development | Not started | Important | Matthew Schuster | Matthew Schuster | 12/13/2021 | 12/08/2021 | 01/03/2022 | false |  |  |  | 0/1 | Ensure any feedback received from initial communication with new style guide has been incorporated | Red
D4lDIVR6s0-u-tokqZqb8GQALREx | Draft communications framework | Communication Strategy Development | Not started | Medium | Matthew Schuster | Matthew Schuster | 12/13/2021 |  | 12/22/2021 | false
I5711RpdSE-8Y7evVfLwimQACc3K | Research and Recommend Tools | Implement Internal Communication Tools | Not started | Medium | Matthew Schuster | Matthew Schuster | 12/13/2021 |  | 12/27/2021 | false
CeGJauCwokmDyusxqj6O82QAJRg- | Develop plan for implementation | Implement Internal Communication Tools | Not started | Medium | Matthew Schuster | Matthew Schuster | 12/13/2021 |  | 12/31/2021 | false | [5 empty] | Green
IGpu2WK4wEeIMYoj7npojWQAEfjh | Conduct UAT for Tools | Implement Internal Communication Tools | Not started | Medium | Matthew Schuster | Matthew Schuster | 12/13/2021 |  | 01/10/2022 | false
O9L6hUNsAUyU3Jv2RnP3A2QAHz_5 | Obtain internal stakeholder buy-in | Communication Strategy Development | Not started | Medium | Matthew Schuster | Matthew Schuster | 12/13/2021 |  | 12/27/2021 | false | [5 empty] | Green
4_l-JAcVlkqqZ-MrL8pAfmQAKR-v | Present to executive leadership | Communication Strategy Development | Not started | Medium | Matthew Schuster | Matthew Schuster | 12/13/2021 |  | 01/12/2022 | false

## Plan name
Plan name | Tasks Test_v1
Plan ID | DN6QFXTlx0q-TP0c-rtFe2QAHtIi
Date of export | 12/13/2021